FRACTIONAL CHIEF AI OFFICER

Engagement Execution Game Plan

Springline Advisory  ·  AI Engagement System

Prepared for:  David O’Hara, Fractional AI Officer - Improving

Counterpart:  Tim Brackney, CEO · Anthony Laria, incoming COO (ran Integration) - Springline Advisory

Commercial basis:  $20,000 / quarter advisory retainer + execution bid per program

Date:  June 18, 2026

Status:  Internal operating plan - not a client deliverable

Contents

# 1. The Job, In One Page

Your mandate is not to deploy AI. It is to make Springline’s AI decisions legible. Twelve federated firms are consolidating onto one Microsoft 365 tenancy and a Snowflake data foundation while the platform keeps acquiring. That integration window is when AI is cheapest to layer onto clean data and hardest to retrofit later. You own the strategy, the sequencing, the governance spine, and the investor narrative so that whenever Trinity Hunt runs its next capital event, the AI portfolio reads in thirty minutes as evidence, not theater.

What you are accountable for Direction - a five-year strategy and a three-year, firm-by-firm roadmap that survives a moving exit date. Discipline - every initiative enters under a stated ROI hypothesis and a capped, fail-fast budget; evidence at the gate decides scale, redesign, or kill. Governance - the audit-logging, data-privacy, HR/policy, and human-approval spine that lets automation cross firm boundaries safely. Narrative - the Realized / In-flight / Optioned snapshot, refreshed at every gate, that the board and the next buyer can underwrite.

What you are NOT accountable for (hold this line) Building the pilots - that is the execution pod, bid per program. Tool procurement, vendor management, and the M365 rollout itself are separate execution scopes with their own ROI hypotheses. The $20K/quarter retainer is the strategy, governance, and narrative layer only.

## Operating Principles You Inherit From the Proposal

- Model-agnostic. Route to the right model across the five partners (OpenAI, Anthropic, Microsoft, Google, AWS). Avoid single-provider lock-in.

- Two parallel portfolios. Efficiency (hard ROI: hours, cost, cycle time) and innovation (upside: proposal velocity, win rate, capacity). Both feed one diligence narrative.

- Planned-hire offset, not headcount cuts. ROI is scored by hires avoided and capacity freed across consolidating firms - the honest math for a talent-constrained roll-up.

- Enterprise tools trail frontier by ~2.5–3 months. Copilot and Cowork lag; sequence around it rather than fighting it.

- Governance gates Stage 4. The program does not cross into composed workflow automation until the governance spine exists. No exceptions.

# 2. Deliverables, Defined

The proposal commits five Q1 advisory deliverables, then a recurring deliverable set each quarter. Below, each is given a concrete definition, the inputs it depends on, and the acceptance criteria that mark it done. Treat the acceptance criteria as your personal definition of complete - they are what you would defend in a board meeting.

## 2.1  Quarter-One Foundation Deliverables

### D1 - Five-Year AI Strategy (through 2031)

What it is: A firm-level strategic narrative for how AI reshapes Springline’s business model, service delivery, and competitive position. It sets the vision everything else is measured against and is the container the board narrative lives inside.

Inputs needed: CEO intent and definition of success; Trinity Hunt’s posture and likely exit window; current service-line economics; the federated-firm maturity map (from discovery).

Acceptance criteria: Approved by Tim; expressed in planned-hire-offset and bi-modal ROI language; explicitly tied to the next capital event; no dependency on a fixed exit date.

### D2 - Three-Year Roadmap (Run / Scale / Reinvent)

What it is: A sequenced, initiative-level plan across the three Horizons with firm-by-firm phasing. Translates strategy to execution and shows stakeholders what happens, when, and in what order.

Inputs needed: Snowflake consolidation status per firm; M365 tenancy state; which firms are most AI-ready vs. most resistant; integration calendar from Anthony Laria.

Acceptance criteria: Each initiative mapped to a Horizon and a target firm/sequence; the first pilots sit where data is cleanest and change management is lightest; the roadmap is explicitly re-sequenceable at each quarterly gate.

### D3 - Prioritized Pilot List with ROI Hypotheses

What it is: A rank-ordered list of Horizon 1 pilots, each with a stated hypothesis, a success metric, and a capped fail-fast budget. This is the capital-allocation tool you carry into the first portfolio gate.

Inputs needed: Discovery workshop output from firm and department leaders; candidate scoring against the bi-modal ROI bar (reference: 5–10x within twelve months, higher for growth bets).

Acceptance criteria: Every pilot has a named owner, a metric baseline, a budget cap, and a gate date; nothing on the list lacks a falsifiable hypothesis; candidates surfaced from discovery, not pre-named.

### D4 - Board & Investor Narrative Draft

What it is: A structured narrative positioning Springline’s AI program for PE diligence and board communication - the Realized / In-flight / Optioned snapshot in presentable form. You own this and refresh it every quarter.

Inputs needed: D1–D3; Trinity Hunt’s diligence expectations; the metrics leadership is under pressure to move before the next cycle.

Acceptance criteria: Readable by a PE buyer in ~30 minutes; classifies the live portfolio by realization state (not a guessed date); is the same story the firm is actually living, so it survives scrutiny.

### D5 - Governance Baseline

What it is: Audit-logging standards, data-privacy controls, HR and policy-compliance rules, and human-approval-point definitions - the precondition for Stage 4 agentic operations across twelve regulated-services firms.

Inputs needed: Access to security, legal, and HR leads; current data-governance state per firm; Snowflake and M365 admin input.

Acceptance criteria: Signed off by security/legal/HR; defines who approves what and where audit trails live; sufficient that no Stage 4 workflow expands without it; aligned to SOC 2-style controls and the alternative-practice (attest/non-attest) separation.

Companion artifact - Reference Architecture v1. The proposal also names a reference architecture in Q1: Azure + Microsoft Foundry as the anchor, Snowflake as the governed data foundation, a model-agnostic orchestration layer on top. You set architectural direction; the Improving delivery pod you pull in owns technical depth. Your acceptance bar: it preserves enterprise controls and data residency while keeping access to the best available model.

## 2.2  Recurring Quarterly Deliverable Set

After Q1, the cadence produces a defined set every quarter. Each gate produces both a deliverable and a funding decision - review and delivery are the same act.

| Quarter | Deliverables | Outcome |
| --- | --- | --- |
| Q1 (kickoff) | 5-yr strategy; 3-yr roadmap; prioritized big rocks; first implement-now pilots selected and started; reference architecture v1; governance baseline; diligence narrative v1 | Strategy set, pilots running, board story drafted |
| Q2 | Pilot evidence and gate decisions; scaled-work scoping from validated data; governance hardened for Stage 4; narrative refresh with early wins | Validated ROI, first scale decisions, sharpened story |
| Q3 | Scaled rollout of proven initiatives; next wave designed; architecture and model-routing updates; diligence pack updated | Operating gains compounding, roadmap extended |
| Q4 / ongoing | Program review vs. KPIs; strategy refresh; readiness pack for investor conversations | Investor-ready position with a running track record |

## 2.3  Horizon Funding Model - Your Allocation Lens

You fund AI as a portfolio drawn from a defined pool, released by horizon in evidence-gated tranches - not against a fixed exit. A quarterly portfolio gate resets the envelopes; a monthly initiative gate releases tranches against evidence.

| Horizon | What it funds | Funding model |
| --- | --- | --- |
| H1 - Run | Operational efficiency and task agents with hard, near-term ROI | Fixed-fee setup + capped fail-fast pilots; targets self-funding from savings |
| H2 - Scale | Workflow automation rolled across firms, once governed | Time & Materials, released from validated H1 evidence |
| H3 - Reinvent | Client-facing growth bets and new service lines with asymmetric upside | Small option-sized probes from a protected pool; few graduate, each cheap to test |

| Snapshot state | Definition | Role in diligence |
| --- | --- | --- |
| Realized | In production and producing measured value | Proof the platform already operates with AI leverage |
| In-flight | Funded and live with early signal | Evidence of momentum and a working delivery engine |
| Optioned | Designed and costed, ready to fund on demand | A defensible roadmap with known economics and triggers |

# 3. The Roadmap

The roadmap moves Springline from the Stage 1–2 boundary (tools adopted, no coordinated strategy) into Wave 2 (process-level, governed automation) over the first 12–18 months, with Wave 3 entering the optioned portfolio as evidence accumulates. Do not overpromise Wave 3 timing.

## Maturity arc

| Wave | Stages | Focus | Where the leverage is |
| --- | --- | --- | --- |
| Wave 1: Tools | 1–2 | Out-of-box M365 + Copilot | Floor, not goal - already licensed |
| Wave 2: Process | 3–4 | Task agents → governed workflows | Near-term center of gravity |
| Wave 3: Agentic Ops | 5–8 | Delegated, orchestrated, client-facing | Optioned now; future state |

The leverage is in the middle of the curve. Stage 2 is paid for; Stage 5+ needs orchestration Springline does not yet need. The near-term return concentrates at the Stage 2→3 and 3→4 boundaries - exactly where Horizon 1 and Horizon 2 operate. Lead with the next two moves, never with Stage 8.

## 18-month sequence

| Window | Horizon focus | Primary moves | Gate output |
| --- | --- | --- | --- |
| Months 0–3 (Q1) | H1 stand-up | Discovery; strategy + roadmap; governance baseline; select & start first pilots in cleanest-data firm | First monthly gates; narrative v1 |
| Months 4–6 (Q2) | H1 → H2 | Run pilots to their gates; kill or scale on evidence; scope scaled work from real data; harden governance for Stage 4 | First scale decisions; narrative v2 |
| Months 7–12 (Q3–Q4) | H2 roll-out | Roll proven workflows across firms; design next wave; refresh architecture & model routing | Compounding gains; investor-ready pack |
| Months 13–18 | H2 deepen / H3 probe | Cross-firm workflow maturity; option-sized H3 probes from protected pool; keep snapshot current | Exit-ready snapshot at any gate |

Sequencing rule of thumb Start where the data is cleanest and the change management is lightest - likely the anchor firm (HM&M Advisory, Dallas) or whichever firm Anthony names as furthest along. A visible win in one firm creates pull from the other eleven. Centralized mandates create resistance; demonstrated wins create demand. This is your antidote to the twelve-veto-point federated trap.

# 4. The First 90 Days

The first quarter is the foundation and the basis for the kickoff. The goal by day 90: strategy set, governance baseline in place, first pilots running against hypotheses, and a board narrative drafted. The plan below runs in four phases.

## Phase 1 - Mobilize & Discover (Weeks 1–3)

Objective: establish the operating relationship, secure access, and surface the real state of the twelve firms before committing to any sequence.

- Week 1 - Charter & access. Confirm the engagement charter with Tim: retainer scope, the monthly/quarterly gate cadence, and the explicit independence statement (arm’s-length B2B despite the shared Trinity Hunt sponsor). Request access to Snowflake/M365 admins and to security, legal, and HR. Establish the weekly working session with Anthony Laria.

- Weeks 1–2 - Discovery workshops. Run structured sessions with firm and department leaders. Where AI sits in the integration roadmap today, who has been driving AI conversations, Snowflake consolidation status per firm, who controls the tech budget, which firms already attempted a pilot and what happened.

- Weeks 2–3 - Maturity map. Place each firm on the 8-stage model. Identify the lead-firm candidate for the first pilot (cleanest data, lightest change management, most willing leader) and the likely resisters to sequence around.

- Week 3 - Definition of success. Lock Tim’s twelve-month definition of success and the specific efficiency or growth metric leadership is under pressure to move before the next diligence cycle. This calibrates what you sequence first.

## Phase 2 - Strategy & Sequencing (Weeks 4–6)

Objective: convert discovery into the strategy, the roadmap, and a scored pilot list.

- Week 4 - Draft the 5-year strategy (D1). Frame in planned-hire-offset and bi-modal ROI language; tie explicitly to the next capital event.

- Weeks 4–5 - Build the 3-year roadmap (D2). Sequence firm-by-firm; treat integration complexity as a design constraint, not a footnote.

- Weeks 5–6 - Score the pilot list (D3). Run candidates through the bi-modal ROI bar. Likely H1 candidates: document processing, compliance-workflow automation, client-onboarding acceleration. Each gets a hypothesis, a metric baseline, a budget cap, and a named owner.

- Week 6 - Strategy review with Tim. Walk D1–D3. Adjust on his input. Secure go-ahead to fund the first H1 tranche.

## Phase 3 - Govern & Launch (Weeks 7–10)

Objective: stand up the governance spine and put the first pilots into motion with the execution pod.

- Weeks 7–8 - Governance baseline (D5). With security/legal/HR: audit-logging standards, data-privacy controls, HR/policy compliance, human-approval points. Account for the attest/non-attest separation. This leads the pilot launches, it does not trail them.

- Weeks 7-8 - Reference architecture v1. Confirm Azure + Foundry anchor, Snowflake data foundation, model-agnostic orchestration. You set direction; the Improving delivery pod owns depth.

- Weeks 8–9 - Pilot kickoff. Hand the top-scored pilots to the execution pod (AI Lead + embedded engineers). Each pilot: stated hypothesis, capped budget, named owner, gate date, instrumentation from day one.

- Weeks 9–10 - First monthly initiative gate. Review earliest signal against hypotheses. Practice the gate ritual now so it is muscle memory by Q2: fund next tranche, scale, pause, or kill.

## Phase 4 - Narrate & Set Cadence (Weeks 11–13)

Objective: produce the board narrative and lock the operating rhythm that carries into Q2.

- Weeks 11–12 - Board & investor narrative draft (D4). Assemble the Realized / In-flight / Optioned snapshot from real funding and delivery evidence. Make it 30-minute-readable.

- Week 12 - First quarterly portfolio gate. Reset horizon envelopes, refresh the roadmap, confirm what continues / scales / stops.

- Week 13 - Q1 readout to Tim (and, if invited, the board). Present the five deliverables and the live pilots. Confirm the Q2 plan and the standing cadence.

90-day exit criteria - what “done” looks like ✓ Five-year strategy and three-year roadmap approved by Tim. ✓ Governance baseline signed off by security, legal, and HR. ✓ At least two H1 pilots live, instrumented, and running against hypotheses in the lead firm. ✓ Board/investor narrative v1 delivered, in Realized/In-flight/Optioned form. ✓ Monthly initiative gate and quarterly portfolio gate both run once - the operating rhythm is real, not theoretical.

# 5. Weekly Time Commitment

The retainer runs on a quarterly cadence with weekly working sessions. The role is senior and advisory - not a full-time seat, and it should not become one. Below is an honest model of the recurring weekly hours, split between the heavier Q1 foundation phase and the lighter steady state from Q2 onward.

## Steady-state week (Q2 onward)

| Activity | Hrs/wk | What it covers |
| --- | --- | --- |
| Springline working session | 1.5 | Standing weekly with Anthony Laria + internal AI owner; progress, blockers, decisions |
| Pilot oversight & gate prep | 2.0 | Reviewing instrumentation, evidence, hypothesis tracking ahead of monthly gates |
| Strategy & roadmap upkeep | 1.5 | Keeping roadmap and sequencing current as firms and evidence move |
| Narrative & snapshot upkeep | 1.0 | Maintaining the Realized/In-flight/Optioned snapshot |
| Improving-side coordination | 1.0 | Sync with the execution pod you pull in; architecture/model-routing decisions |
| Stakeholder & ad-hoc | 1.0 | CEO check-ins, firm-leader relationship work, unplanned items |
| TOTAL (steady state) | ~8 | Roughly one day per week |

## Q1 foundation week (Weeks 1–13)

| Activity | Hrs/wk | What it covers |
| --- | --- | --- |
| Discovery & stakeholder access | 3.0 | Workshops across firms/departments; securing admin and security/legal/HR access |
| Deliverable authoring (D1–D5) | 5.0 | Drafting strategy, roadmap, pilot list, governance baseline, narrative |
| Pilot setup & pod coordination | 2.0 | Standing up pilots, hypotheses, instrumentation with the execution pod |
| Working sessions & reviews | 2.0 | Weekly session + strategy/gate reviews with Tim and Anthony |
| TOTAL (Q1) | ~12 | Roughly 1.5 days per week during foundation |

Time-commitment read Plan for ~12 hrs/week in Q1, settling to ~8 hrs/week (about one day) in steady state. Two demand spikes recur: the monthly initiative gate (add ~2–3 hrs that week) and the quarterly portfolio gate plus board readout (add ~6–8 hrs that week). If weekly hours creep well past this, it is a signal that execution scope is bleeding into the advisory retainer - re-bid it as a program rather than absorbing it.

# 6. Who You Engage on the Springline Side

Success depends on a small set of named relationships and timely access to a few functions. The proposal’s own assumptions make this explicit: timely access to firm/department leaders for discovery, to Snowflake and M365 admins for provisioning, and to security, legal, and HR for governance - plus active participation in the monthly and quarterly gates.

## Core relationships

| Who | Role | Why they matter to you | Cadence |
| --- | --- | --- | --- |
| Tim Brackney | CEO | Your principal. Owns the vision, the board relationship, and the definition of success. A COO-pedigreed operator (ex-President/COO, RGP ~$700M) who expects rigor and quarterly measurement. | Monthly 1:1 + quarterly gate / readout |
| Anthony Laria | Incoming COO (ran Integration) | Your day-to-day execution partner and the operational spine of the firm. Owns how acquired firms absorb change; his integration calendar shapes the roadmap as much as Tim’s priorities. | Weekly working session |
| Internal AI owner | TBD (may not exist yet) | If one exists, you augment and accelerate - not replace. If not, flag the gap early; you need a day-to-day counterpart inside Springline. | Weekly / as stood up |
| Improving delivery pod | Execution capability you pull per build cycle (AI lead + embedded engineers) | Not a co-lead. You are the sole Fractional CAIO and own strategy, governance, and narrative; the pod builds and instruments pilots against your hypotheses, bid per program. | Per build cycle |

## Functional access you need

| Function | What you need from them | When |
| --- | --- | --- |
| Snowflake & M365 admins | Environment provisioning, data-foundation state per firm, tenancy status | Weeks 1–8 |
| Security & IT | Controls baseline, audit-logging standards, data residency | Weeks 7–8 (governance) |
| Legal | Data-privacy controls, NDA/confidentiality boundaries, attest/non-attest separation | Weeks 7–8 |
| HR | Policy compliance, change-management posture, workforce-impact framing | Weeks 7–8 |
| Firm & department leaders | Discovery input, pilot candidates, lead-firm selection | Weeks 1–3, then per pilot |

## Background stakeholder - Trinity Hunt Partners

Trinity Hunt (Davis Fox, VP) backs both Springline and Improving and made the original introduction. Treat the shared sponsor as a trust accelerant, not a closing lever. It warms the relationship and gives the engagement implicit support, but the work must stand on its own merits and the engagement must remain visibly arm’s-length. You will help Springline state that independence clearly to its team and stakeholders. Trinity Hunt’s interest in a differentiated asset at exit is the real reason the investor-narrative deliverable matters.

## Political landscape to manage

- Federated veto points. Twelve firms with independent partners means twelve potential blockers. Win one firm visibly, let pull do the work across the rest.

- Budget control. Determine early whether tech budget is centralized or federated - it changes how you fund and sequence pilots.

- Prior AI attempts. Find out which firms already tried a pilot and what the organizational memory is. You are building on - or recovering from - that narrative.

- Culture-first CEO. Tim treats people-first culture as the competitive differentiator. Frame AI in employee-experience and capacity terms, not headcount reduction - it is also the honest ROI math here.

# 7. Risks to Manage From Day One

| Risk | Signal | Your move |
| --- | --- | --- |
| Scope creep into the retainer | “Can you also run the M365 rollout / manage vendors?” | Hold the line: that is a separate execution bid with its own ROI hypothesis. Retainer = strategy, governance, narrative. |
| Federated resistance | A firm’s partners stall or refuse a pilot | Re-sequence to a willing firm; use the win to create pull. Never force a centralized mandate first. |
| Governance lag | Pressure to launch Stage 4 workflows before controls exist | Refuse to cross the Stage 4 gate without the baseline. It is the one non-negotiable. |
| Exit-timing whiplash | Plan anchored to a single close date | Keep the horizon funding model - envelopes, not dates. The snapshot stays current at month 9, 15, or 24. |
| Internal-hire ambiguity | Springline hires its own AI lead | Reframe to augment-and-accelerate, not replace. Define the division of labor explicitly. |
| Over-leaning on shared PE backer | Relationship used as pressure | Use it for warmth and context once; let the proposal stand on merits. Keep independence visible. |

Bottom line. Your first 90 days buy the right to the next 90. If by day 90 the strategy is approved, the governance spine is in place, two pilots are running on real hypotheses, and Tim is holding a narrative he can take to Trinity Hunt - you have proven the model and earned the cadence. Everything after that is the loop tightening quarter over quarter.