Steve Hall AI Project

Internal Kickoff Guide

Team Guidance & Process Checklist

February 2026

INTERNAL USE ONLY

# Kickoff Overview

This document is the internal playbook for launching the Steve Hall AI Implementation engagement. It covers the kickoff meeting structure, data discovery process, team roles, weekly cadence, and checklists to keep us on track. The client-facing project plan has been delivered separately.

- Client: Steve Hall — automotive dealerships (Denver Bentley, Honda of Paris), auto finance company, foundation

- Engagement Lead: David O’Hara, Regional Director (nonbillable)

- Account Executive: Derek Nwamadi, Senior Account Executive

- Platform: Google Workspace (Gmail, Calendar, Drive) — already established

- Baseline Product: Improving Executive System (IES) — deployed locally via Claude Cowork + Google Workspace MCP Connectors

- Engagement Model: Time & Materials — Phase 1 SOW with NTE cap

- Principal Technologist Rate: $200/hr

- Phase 1 Target Timeline: 3–4 weeks

# Step 1: Data Discovery Kickoff Meeting

Schedule a 2-hour working session with Steve and any key team members who manage his systems. This is the single most important meeting of the engagement — everything downstream depends on what we learn here.

## Meeting Logistics

☐ Schedule within 1 week of engagement start

☐ Duration: 2 hours (block 2.5 to account for overrun)

☐ Attendees: Steve Hall, David O’Hara, Principal Technologist, any Steve-side IT or admin contacts

☐ Format: In-person preferred (both in Dallas); video call acceptable

☐ Pre-read: Send Steve the client-facing project plan 48 hours before the meeting

## Kickoff Agenda

- Introductions & Engagement Overview (10 min) — Confirm Phase 1 scope, timeline, T&M terms, NTE cap

- Current Tools & Systems Walkthrough (40 min) — Steve walks us through every system he touches daily

  - Email client(s)? Confirm Gmail / Google Workspace setup

  - Calendar system — Google Calendar confirmed; any secondary calendars?

  - Document storage — Google Drive; any Dropbox, OneDrive, or local file shares?

  - DMS — which vendor? (Reynolds & Reynolds, CDK, Tekion, other)

  - Accounting/ERP — what runs the books at each entity?

  - Auto finance loan management platform

  - How does Steve receive acquisition target financials?

  - Foundation website / CMS platform

  - Voice memos — does Steve use them today? What device/app?

- Access & Permissions Discussion (20 min) — What can we connect to, and how?

- Priority Alignment (20 min) — Confirm which Phase 1 use cases matter most to Steve right now

- Next Steps & Timeline Confirmation (10 min)

⚠️ Critical Questions to Answer in This Meeting • Which DMS platform does each dealership use? • Where do board decks and strategic briefs live? (Google Drive? Shared drive?) • How is acquisition pipeline data received and stored? • Does Steve use voice memos today? What device / app? • Who are the 2–3 operators Steve coaches most frequently? • What does the foundation’s content workflow look like today?

# Step 2: Inventory Current Tools & Access

Within 48 hours of the kickoff meeting, compile the complete system inventory. This becomes the Integration Feasibility Matrix — the blueprint for Phase 1 connectors and the Phase 2 backlog.

## Phase 1 Systems (Google Workspace)

☐ Gmail — confirm account(s), verify API access scopes

☐ Google Calendar — confirm primary + any shared calendars

☐ Google Drive — map folder structure for key documents

☐ Google Contacts — verify export/API access

## Phase 2 Systems (Discovery — Document for Future SOW)

Business Systems

☐ DMS platform identified and API documentation obtained

☐ Accounting/ERP systems catalogued per entity

☐ Auto finance loan platform access confirmed

☐ CRM system identified (if any beyond email)

Market & Intelligence Sources

☐ SEC EDGAR API access confirmed (free, no auth required)

☐ Automotive data feed options evaluated (NADA, Cox, KBB)

☐ Financial news source selected (Bloomberg, Reuters, alternatives)

Content & Operations

☐ Foundation CMS platform identified

☐ Existing publications and voice samples collected

☐ Event management tool for Wisdom Dinners documented

## Feasibility Rating

Rate each system on a simple matrix:

| Rating | API Status | Effort | Action |
| --- | --- | --- | --- |
| ✅ Green | Public API or OAuth | < 1 week | Standard MCP connector |
| ⚠️ Yellow | API exists, limited docs | 1–2 weeks | Custom MCP server needed |
| 🛑 Red | No API / manual only | 2–4 weeks | ETL pipeline or workaround |

# Step 3: Deliver Integration Roadmap

By end of Week 2, deliver the formal integration roadmap to Steve. This is our first tangible deliverable and sets expectations for Phase 2 scope.

## Deliverables Checklist

☐ Data Landscape Map — visual diagram showing all systems, data flows, and access methods

☐ Integration Feasibility Matrix — each source rated green/yellow/red with effort estimates

☐ Phase 2 Connector Backlog — prioritized list of custom integrations, ordered by business value

☐ Security & Access Architecture — authentication strategy, data handling policies

Review this package with Steve in a 30-minute session. Get explicit sign-off before confirming the Phase 2 SOW scope.

# Step 4: Phase 1 Build

Phase 1 is the IES deployment with core use cases. The goal is to get Steve using the system daily within the first week. This is our proving ground — if Phase 1 doesn’t land, Phase 2 doesn’t happen.

## Build Priorities (in order)

- IES + Google Workspace MCP setup — deploy IES locally via Claude Cowork; connect to Gmail, Calendar, and Drive via MCP connectors

- Voice training — analyze 3–6 months of sent email to learn Steve’s communication style

- Email response drafting — first AI-drafted email within 48 hours of deployment

- Morning briefing — automated daily summary of calendar, priorities, pending items by 6:00 AM

- To-do tracking & calendar intelligence — capture commitments from email/calendar, flag overdue items

- Voice-to-draft workflow — set up dictation capture pipeline for white paper and foundation content

- Email & time intelligence — communication pattern analysis, time allocation vs. priorities

- Foundation content drafting — white papers and Stewardship Mandates in Steve’s voice

## First-Week Success Metrics

☐ Steve receives first AI-drafted email response within 48 hours of build start

☐ Morning briefing delivered by 6:00 AM on Day 3

☐ Steve provides feedback on at least 5 AI drafts for voice calibration

☐ System handles at least 50% of routine email responses by end of week

🎯 Phase 1 Is the Proving Ground • If Steve doesn’t use it daily within the first week, we need to course-correct immediately • Daily check-in with Steve for the first 5 days — tune voice, adjust priorities, fix friction • Don’t over-engineer. Ship rough drafts and iterate based on Steve’s feedback • Goal: Steve says “I can’t go back to doing this manually” • Phase 1 success = Phase 2 SOW. Don’t lose momentum.

# Step 5: Establish Weekly Review Cadence

Set up a standing 30-minute weekly review with Steve. This is how we maintain alignment, adjust priorities, and plan the next sprint. Protect this meeting — cancellations compound into drift.

## Weekly Review Agenda Template

- Quick Wins Review (5 min) — What worked well this week? What saved Steve time?

- Friction Report (5 min) — Where did the AI get it wrong? What needs tuning?

- Usage Metrics (5 min) — Emails drafted, time saved, adoption indicators

- Next Sprint Plan (10 min) — What are we building next? Any priority changes?

- Open Items (5 min) — Blockers, access requests, decisions needed from Steve

## Internal Team Sync

- Monday: Plan the week’s build priorities based on Friday’s review with Steve

- Thursday: Check progress, surface blockers before Friday review

- Use a shared Slack channel or Teams thread for async updates between syncs

# Risks & Escalation Paths

| Risk | Impact | Mitigation | Escalate To |
| --- | --- | --- | --- |
| Steve low adoption Week 1 | Undermines entire engagement | Daily check-ins, reduce friction, simplify outputs | David immediately |
| Google API access issues | Blocks IES deployment | Pre-clear OAuth scopes with Steve before build | Tech Lead → Steve |
| Voice/tone calibration slow | Steve loses confidence in drafts | Use smaller corpus, more manual tuning sessions | Tech Lead |
| DMS has no API | Blocks Phase 2 financial agents | Document in Phase 2 backlog; evaluate alternatives | David + Tech Lead |
| Scope creep from enthusiasm | Phase 1 timeline slips, NTE risk | Document in Phase 2 backlog, defer to next SOW | Derek (scope mgmt) |
| Data sensitivity concerns | Steve hesitant to grant access | Review security architecture, emphasize local deployment | David → Steve |

# Master Kickoff Checklist

Use this as the single source of truth. Check off items as completed. Review at every internal standup.

## Pre-Kickoff

☐ MSA signed by both parties

☐ Phase 1 NTE estimate approved by Steve

☐ Client-facing project plan delivered to Steve

☐ Kickoff meeting scheduled (2-hour block)

☐ Pre-read sent to Steve 48 hours before meeting

☐ Internal team briefed on Steve’s portfolio and use cases

☐ Principal Technologist assigned and briefed

## Kickoff Meeting

☐ All critical systems identified and documented

☐ DMS platform confirmed (for Phase 2 planning)

☐ Data sensitivity and access requirements understood

☐ Steve’s Phase 1 priority use cases confirmed

☐ Next steps and timeline agreed

## Post-Kickoff (Within 48 Hours)

☐ Google Workspace API access granted and tested

☐ System inventory compiled

☐ Integration Feasibility Matrix drafted

☐ Phase 2 connector backlog created

## Week 1 of Build

☐ IES deployed locally via Claude Cowork with Google Workspace MCP connectors

☐ Voice training initiated on sent email corpus

☐ First AI-drafted email delivered to Steve

☐ Morning briefing operational

☐ Weekly review cadence established with Steve

## Weeks 2–4

☐ All Phase 1 use cases operational (email, to-do, voice-to-draft, calendar, intelligence, content)

☐ Integration roadmap delivered and signed off by Steve

☐ Phase 1 success criteria met

☐ Internal retrospective on Phase 1 completed

☐ Phase 2 SOW drafted based on discovery findings

☐ Phase 2 SOW reviewed with Steve for approval