Steve Hall AI Project

Internal Kickoff Guide

Team Guidance & Process Checklist

February 2026

INTERNAL USE ONLY

# Kickoff Overview

This document is the internal playbook for launching the Steve Hall AI Implementation engagement. It covers the kickoff meeting structure, data discovery process, team roles, weekly cadence, and checklists to keep us on track. The client-facing project plan has been delivered separately.

Client: Steve Hall — automotive dealerships (Denver Bentley, Honda of Paris), auto finance company, foundation

Engagement Lead: David O’Hara, Regional Director

Platform: Google Workspace (Gmail, Calendar, Drive) — already established

Baseline Product: Improving Executive System (IES) — deployed locally via Claude Cowork + Google Workspace MCP Connectors

Target Timeline: 4–5 weeks total with sequential execution

# Step 1: Data Discovery Kickoff Meeting

Schedule a 2-hour working session with Steve and any key team members who manage his systems. This is the single most important meeting of the engagement — everything downstream depends on what we learn here.

## Meeting Logistics

☐  Schedule within 1 week of engagement start

☐  Duration: 2 hours (block 2.5 to account for overrun)

☐  Attendees: Steve Hall, David O’Hara, technical lead, any Steve-side IT or admin contacts

☐  Format: In-person preferred; video call acceptable

☐  Pre-read: Send Steve the client-facing project plan 48 hours before the meeting

## Kickoff Agenda

- Introductions & Engagement Overview (10 min) — Confirm scope, timeline, phased approach

- Current Tools & Systems Walkthrough (40 min) — Steve walks us through every system he touches daily

  - What email client(s)? Confirm Gmail / Google Workspace setup

  - Calendar system — Google Calendar confirmed; any secondary calendars?

  - Document storage — Google Drive; any Dropbox, OneDrive, or local file shares?

  - Dealer Management System — which vendor? (Reynolds & Reynolds, CDK, Tekion, other)

  - Accounting/ERP — what runs the books at each entity?

  - Auto finance loan management platform

  - How does Steve receive acquisition target financials?

  - Foundation website / CMS platform

  - Event management for Wisdom Dinners

  - Contractor communication tools (Dallas renovation)

- Access & Permissions Discussion (20 min) — What can we connect to, and how?

  - API availability for each system

  - Authentication methods (OAuth, API keys, service accounts)

  - Data sensitivity levels and handling requirements

  - Who approves access at each entity?

- Priority Alignment (20 min) — Confirm which use cases matter most to Steve right now

- Next Steps & Timeline Confirmation (10 min)

⚠️ Critical Questions to Answer in This Meeting • Which DMS platform does each dealership use? • Where do board decks and strategic briefs live? (Google Drive folder? Shared drive?) • How is acquisition pipeline data received and stored? • Does Steve use voice memos today? What device / app? • Who are the 2–3 operators Steve coaches most frequently? • What does the foundation’s content workflow look like today?

# Step 2: Inventory Current Tools & Access

Within 48 hours of the kickoff meeting, compile the complete system inventory. This becomes the Integration Feasibility Matrix — the blueprint for every connector we build.

## System Inventory Checklist

Google Workspace (Confirmed)

☐  Gmail — confirm account(s), verify API access scopes

☐  Google Calendar — confirm primary + any shared calendars

☐  Google Drive — map folder structure for key documents

☐  Google Contacts — verify export/API access

Business Systems (Discovery)

☐  DMS platform identified and API documentation obtained

☐  Accounting/ERP systems catalogued per entity

☐  Auto finance loan platform access confirmed

☐  CRM system identified (if any beyond email)

Market & Intelligence Sources

☐  SEC EDGAR API access confirmed (free, no auth required)

☐  Automotive data feed options evaluated (NADA, Cox, KBB)

☐  Financial news source selected (Bloomberg, Reuters, alternatives)

☐  Interest rate data source confirmed (FRED, Treasury Direct)

Content & Operations

☐  Foundation CMS platform identified

☐  Event management tool for Wisdom Dinners documented

☐  Contractor communication channels mapped (renovation)

☐  Existing publications and voice samples collected

## Feasibility Rating

Rate each system on a simple matrix:

| Rating | API Status | Effort | Action |
| --- | --- | --- | --- |
| ✅ Green | Public API or OAuth | < 1 week | Standard connector |
| ⚠️ Yellow | API exists, limited docs | 1–2 weeks | Custom connector needed |
| 🛑 Red | No API / manual only | 2–4 weeks | ETL pipeline or workaround |

# Step 3: Deliver Integration Roadmap

Within 2 weeks of engagement start, deliver the formal integration roadmap to Steve. This is our first tangible deliverable and sets expectations for the entire build.

## Deliverables Checklist

☐  Data Landscape Map — visual diagram showing all systems, data flows, and access methods

☐  Integration Feasibility Matrix — each source rated green/yellow/red with effort estimates

☐  Connector Development Backlog — prioritized list of custom integrations, ordered by phase dependency

☐  Security & Access Architecture — authentication strategy, data handling policies, encryption requirements

Review this package with Steve in a 30-minute session. Get explicit sign-off before proceeding to Phase 1 build.

# Step 4: Begin Phase 1 Build

Phase 1 is the IES deployment. The goal is to get the Improving Executive System running locally on Steve’s hands with MCP connectors into Google Workspace within the first few days. This is our proving ground — if Phase 1 doesn’t land, the rest doesn’t happen.

## Build Priorities (in order)

- IES + Google Workspace MCP setup — deploy IES locally via Claude Cowork; connect to Gmail, Calendar, and Drive via MCP connectors

- Voice training — analyze 3–6 months of sent email to learn Steve’s communication style

- Morning briefing — automated daily email summarizing calendar, priorities, pending items

- Calendar intelligence — meeting prep, conflict detection, scheduling assistance

- Voice-to-draft workflow — set up dictation capture pipeline for white paper content

## First-Week Success Metrics

☐  Steve receives first AI-drafted email response within 48 hours of build start

☐  Morning briefing delivered by 6:00 AM on Day 3

☐  Steve provides feedback on at least 5 AI drafts for voice calibration

☐  System handles at least 50% of routine email responses by end of week

🎯 Phase 1 Is the Proving Ground • If Steve doesn’t use it daily within the first week, we need to course-correct immediately • Daily check-in with Steve for the first 5 days — tune voice, adjust priorities, fix friction • Don’t over-engineer. Ship rough drafts and iterate based on Steve’s feedback • Goal: Steve says “I can’t go back to doing this manually”

# Step 5: Establish Weekly Review Cadence

Set up a standing 30-minute weekly review with Steve. This is how we maintain alignment, adjust priorities, and plan the next sprint. Protect this meeting — cancellations compound into drift.

## Weekly Review Agenda Template

- Quick Wins Review (5 min) — What worked well this week? What saved Steve time?

- Friction Report (5 min) — Where did the AI get it wrong? What needs tuning?

- Usage Metrics (5 min) — Emails drafted, time saved, adoption indicators

- Next Sprint Plan (10 min) — What are we building next? Any priority changes?

- Open Items (5 min) — Blockers, access requests, decisions needed from Steve

## Internal Team Sync

In addition to the Steve-facing weekly review, run a 15-minute internal standup twice a week:

- Monday: Plan the week’s build priorities based on Friday’s review with Steve

- Thursday: Check progress, surface blockers before Friday review

- Use a shared Slack channel or Teams thread for async updates between syncs

# Risks & Escalation Paths

| Risk | Impact | Mitigation | Escalate To |
| --- | --- | --- | --- |
| DMS has no API | Blocks Phase 3 financial agents | Evaluate screen scraping or data export pipeline | David + Tech Lead |
| Steve low adoption in Week 1 | Undermines entire engagement | Daily check-ins, reduce friction, simplify outputs | David immediately |
| Data access denied by Steve’s IT | Delays connector builds | Escalate to Steve for authorization | David → Steve |
| Voice/tone calibration takes too long | Steve loses confidence in drafts | Use smaller corpus, more manual tuning sessions | Tech Lead |
| Scope creep from Steve’s enthusiasm | Timeline slips, team overloaded | Document in backlog, defer to next phase | David (scope management) |

# Master Kickoff Checklist

Use this as the single source of truth. Check off items as completed. Review at every internal standup.

Pre-Kickoff

☐  Client-facing project plan delivered to Steve

☐  Kickoff meeting scheduled (2-hour block)

☐  Pre-read sent to Steve 48 hours before meeting

☐  Internal team briefed on Steve’s portfolio and use cases

Kickoff Meeting

☐  All critical systems identified and documented

☐  DMS platform confirmed

☐  Data sensitivity and access requirements understood

☐  Steve’s priority use cases confirmed

☐  Next steps and timeline agreed

Post-Kickoff (Within 48 Hours)

☐  System inventory compiled

☐  Integration Feasibility Matrix drafted

☐  Connector development backlog created

☐  Access requests submitted for all systems

Week 1 of Build

☐  IES deployed locally via Claude Cowork with Google Workspace MCP connectors

☐  Voice training initiated on sent email corpus

☐  First AI-drafted email delivered to Steve

☐  Morning briefing operational

☐  Weekly review cadence established with Steve

Week 2+

☐  Phase 1 success criteria met

☐  Integration roadmap delivered and signed off

☐  Phase 2 build started (Intel, Content & Research)

☐  Phase 3 build started after Phase 2 (Financial Intelligence)

☐  Internal retrospective on Phase 1 completed